# 0148 Preliminaries – ABIC EW-1

Worksection abstract

This worksection Template is applicable to the ABIC EW-1 contract for early works. It is relevant to the site requirements of the owner. The project specific version may include site security arrangements, occupancy constraints, adjoining properties constraints, other temporary facilities, project signage, provisional sums, requirements for progress photographs, authority requirements, survey requirements, separate contracts, some aspects of cost adjustment, and pest eradication.

Background

NATSPEC also provides preliminaries for ABIC BW 2018 C, ABIC SW-2018, ABIC MW-2018, AS 2124, AS 4000, AS 4902, AS 4905 and NCW4 contracts.

Refer to NATSPEC TECHnote GEN 016 for information on the differences between the general conditions of contract and the specification preliminaries.

Special conditions are provided for commercial and industrial projects in Queensland and for housing projects in all states and territories except Queensland.

How to use this worksection

This worksection Template must be customised for each project. See A guide to NATSPEC worksections (www.natspec.com.au) for information on Template structure, word styles, and completing a worksection.

Related material located elsewhere in NATSPEC

If a listed worksection is not part of your subscription package and you wish to purchase it, contact NATSPEC.

Related material may be found in other worksections. See for example:

0121 Tendering.

0160 Quality and any relevant provisions in the contract for quality assurance.

0171 General requirements.

0172 Environmental management for environmental protection.

0201 Demolition for disposal of demolished materials.

0242 Landscape – fences and barriers for temporary fencing.

Cross references

Worksections that cross reference this worksection are:

None.

Material not included in NATSPEC

Some projects may include items not covered by NATSPEC. For these you may need to create new text, or modify this text or a suitable worksection. For example:

On incorporation of the owner’s policies (e.g. apprentice employment, prohibition of smoking, union labour employment, existing site allowances, procurement policies, insurance arrangements).

The standard preliminaries of many public works authorities include clauses on policy. This worksection includes some prompts but no text.

The contractor’s preliminaries e.g. scaffolds, lunch sheds, cranes, site security.

Documenting this and related work

You may document this and related work as follows:

This worksection is intended for use with, and affects the execution of, all technical worksections of the project specification.

The contents of this worksection should be drawn to the attention of other project consultants for coordination. The contents of this worksection should also be brought to the attention of identified subcontractors, via the identified subcontract preliminaries.

This worksection should be read in the context of the general conditions of contract, any special conditions of contract, and any separately specified quality assurance requirements.

An outline description of the works should be located in ABIC EW-1 at Introduction, Item 6, and the listing of contract documents should be located in ABIC EW-1 at Schedule 3.

Consider incorporating development approval conditions that are the responsibility of the contractor.

For quality assurance (QA), see 0160 Quality – though the contract does not anticipate use of QA. However, because quality assurance affects fundamentally the roles and responsibilities of the architect, contractor and owner, it may be that conventional forms of contract (such as ABIC BW 2018 C) are not suitable where QA is required. If concerned, seek advice on this matter.

The Normal style text of this worksection may refer to items as being documented elsewhere in the contract documentation. Make sure they are documented.

Search acumen.architecture.com.au, the Australian Institute of Architects’ practice advisory subscription service, for notes on the following:

ABIC contracts.

Adverse possession - ensuring the building is on the right site.

Birds and buildings.

Clerk of works.

Contract preparation - for incorporation of government policy.

Contract administration.

Lead hazards in construction.

Meetings.

Negotiated contracts.

Noise from building sites.

Project records.

Work health and safety (WHS).

Referencing standard documents.

Safety in design.

Site surveys and survey types.

Statutory approvals.

## General

For general material, essential to the use and interpretation of the NATSPEC technical worksections, see 0171 General requirements.

### General

See ABIC EW-1 Section A.

#### General conditions

Requirement: To ABIC EW-1 Early Works Contract, issued by the Royal Australian Institute of Architects and Master Builders Association.

This reference properly belongs in 0121 Tendering. Include here only if 0121 Tendering is not used.

To make sure the specification has contractual force, identify the specification by title, date of issue and/or issue number in ABIC EW-1 at Schedule 3.

#### Interpretation

See ABIC EW-1 Section S.

General: The words principal and contract administrator have the same meaning, respectively, as owner and architect, unless the context requires otherwise.

The ABIC EW-1 forms use the terms architect, owner, and contractor as does this worksection. However, NATSPEC technical worksections use the terms principal and contract administrator, as these have more general application. If the terms owner and architect are also used throughout the project specification (e.g. by global change to the NATSPEC worksections), this clause is unnecessary and should be deleted.

Cross reference: INTERPRETATION in 0171 General requirements, also applies.

### The site

See ABIC EW-1 Section F.

If included in ABIC EW-1 Schedule 4, site information should not also be included here. Alternatively, if including site information here, reference the relevant clauses in Schedule 4.

#### Site restrictions

You may need to consider and document the following:

Jackhammer and compressor silencing: See AS 2436, on construction site noise control.

Waste management: Proposals may be sought from the contractor. However, toxic waste disposal may need to be specified. Waste minimisation is in the owner’s interest, providing the savings in cost and time are passed on.

Fumes.

Fauna.

Fire protection.

Erosion control.

Smoke.

Disposal of contaminants, particularly solvents and cement runoff.

Disposal of waste, including food scraps and site waste.

Cleaning of trucks before leaving the site (e.g. if the site is infested with dieback).

Dust control measure, such as full time provision of a water truck. This may be required for major civil engineering works, otherwise the measures used to meet the performance requirement should be the responsibility of the contractor.

Further to the owner’s obligation to give site information to the contractor, the owner may also need to warrant that there is no toxic waste or asbestos on site, for example.

Site limitations: Comply with the following restrictions on the use of the site:

If not shown on the drawings, give details of easements, restrictions arising out of the actions of adjoining land owners, limitations related to continued occupancy by the owner, toxic ground conditions and the like, including maximum noise levels and hours of work not covered by local authority conditions in the Authority conditions schedule.

Access: Access onto and within the site, use of the site for temporary works and constructional plant, including working and storage areas, location of offices, workshops, sheds, roads and parking, is restricted to the following areas:

e.g. Shown on drawing A001, To be determined.

#### Occupied premises

See ABIC EW-1 clauses F1 and F2 on possession and access to the site.

General: For the parts of the site designated as occupied premises in the Occupied premises schedule:

Allow occupants to continue in secure possession and occupancy of the premises for the required period.

Maintain safe access for occupants.

Arrange work to minimise nuisance to occupants and for their safety.

Protect occupants against weather, dust, dirt, water or other nuisance.

Proposals: Submit details of proposed methods.

Purpose of submission: Information only.

#### Occupied premises schedule

| Occupants | Occupied premises | Period of occupancy |
| --- | --- | --- |

Complete the schedule if the owner or occupants authorised by the owner will remain in possession of part of the site.

Occupants: e.g. The owner, The owner’s department, The public, or name other persons or organisations.

Occupied premises: Describe, or refer to marked areas on the drawings.

Period of occupancy: e.g. Duration of the contract.

#### Protection of persons and property

Temporary works: Provide and maintain required hoardings, barricades, guards, fencing, shoring, temporary roadways, footpaths, signs, lighting and traffic management.

Edit to complement local authority requirements scheduled in MISCELLANEOUS, Authority conditions schedule. This paragraph should describe the owner’s requirements only. If a specific hoarding is required document type and location The responsibility for these items is usually the contractor’s.

Accessways, services: Do not obstruct or damage roadways and footpaths, drains and watercourses and other existing services in use on or adjacent to the site. Determine the location of such services.

Delete if documented in the Authority conditions schedule.

Property: Do not interfere with or damage trees and property which are to remain on or adjacent to the site, including adjoining property encroaching onto the site.

Control of runoff stormwater:

Generally, the contractor’s responsibility. Delete or describe here any particular requirements of the owner.

#### Rectification

Accessways, services: Rectify immediately any obstruction or damage to roadways and footpaths, drains and watercourses and other existing services in use on or adjacent to the site. Provide temporary services whilst repairs are carried out.

Property: Rectify immediately any interference or damage to trees and property which are to remain on or adjacent to the site, including adjoining property encroaching onto the site.

Delete if rectification is included in the Authority conditions schedule. See also 0172 Environmental management.

#### Existing services

Service to be continued: Repair, divert or relocate service, as documented.

Trenches: If the existing service crosses the line of a required trench or will lose support when the trench is excavated, provide permanent support for the existing service.

Redundant services: Remove redundant parts and make safe.

Interruptions to services: Minimise the number and duration of interruptions.

Proposals: Submit proposals for action to be taken to existing services before starting this work.

Purpose of submission: For review.

#### Adjoining property

Notice: At least 10 working days before commencing work, submit to owners and occupants of adjoining property written notice of intention to commence work and an outline description of the type and extent of work.

Conditions for work on adjoining property:

The owner is responsible for obtaining permission from adjoining owners, including for work such as swinging crane jibs, erection of scaffolding and construction of formwork. Describe any conditions that may have been agreed to by the owner.

Revealed encroachments: If the works reveal unknown encroachments of adjoining property on to the site or of existing site structures on to adjoining property, immediately seek instructions.

Records: For each property described in the Adjoining properties to be recorded schedule:

Inspect the property with the architect and owner and occupant of the property, before commencement of work.

Make detailed records of conditions existing within the property, especially structural defects and other damage or defacement.

Arrange for at least 2 copies of each record, including drawings, written descriptions, and photographs, to be endorsed by the owner and occupant of the property, or their representatives, as evidence of conditions existing before commencement of work.

Endorsed copies: Submit one endorsed copy of each record. Keep the other endorsed copy on site.

Purpose of submission: Information only.

#### Adjoining properties to be recorded schedule

| Title | Owner | Description |
| --- | --- | --- |

Complete the schedule if there is danger of damage to adjoining property, including the owner’s own, and if precautionary inspections and records need to be made.

### Construction plant

#### Use of existing services

General: Existing services may be used as temporary services for the performance of the contract subject to conditions, as documented in the Existing services schedule.

#### Existing services schedule

| Service | Conditions of use |
| --- | --- |

If existing services, including telephones or permanent building lighting, may be used for contract purposes, list them here and state any conditions applying to their use, e.g. The existing water service on the site, at no charge, Do not disrupt continuous service to owner, Pay for connections, Provide separate metering and reimburse owner, Fully maintain the service.

#### Protective clothing

Rubber boots, safety boots, safety glasses and gloves are also often required on building sites, but it is perhaps unreasonable to expect the contractor to supply them in a full range of sizes to visitors without charge and without notice. Architects should provide properly fitting protective clothing for their own use.

Protective clothing: Make available protective clothing for the use of visitors, as follows:

Safety helmets: To AS/NZS 1801, Type 1.

Certification provider: Submit product certification from an organisation accredited by the Joint Accreditation System of Australia and New Zealand (JAS-ANZ).

Number of helmets:

#### Temporary services

Requirement:

Temporary services are generally the responsibility of the contractor. If it is necessary to specify particular requirements, do so here, e.g. temporary services for owner’s facilities if construction activities interfere, power for testing, temporary distribution boards, special lighting requirements, water for testing, metering and payments for services.

#### Temporary fence

Requirement:

Provide text only if a fence is required by the owner, for example, to secure occupied premises. Normally site security is the responsibility of the contractor. Document in 0242 Landscape – fences and barriers for example, and cross reference, or document here. Requirements of regulatory authorities may conflict. Note that hoardings are generally a local authority requirement and need not be documented in most circumstances.

#### Project signboards

General: Provide project-specific signboards and as follows:

Locate where directed.

Maintain in good condition for duration of the work.

Obtain permission for removal.

Remove on completion.

Other signboards: Obtain approval before display of advertisements or provision of other signboards.

#### Project signboard description

Best shown on the drawings. Components may be provided by the architect – modify as required.

Location:

Size:

Text, graphics:

e.g. Name of the project, the owner, contractor, architect, engineer, quantity surveyor.

Other details:

e.g. Drawing number.

### Building the works

See ABIC EW-1 Section G.

#### Surveys

Edit Surveys if instructions are required additional to those in ABIC EW-1 clause G1 and G2 e.g. employment of a licensed surveyor to check tolerances of structural elements such as position of columns, verticality of columns and facades, and floor levels. Also, provision of equipment and labour to assist checks by the architect.

Setting out:

See ABIC MW-2018 clause. G2 Additional information required here may include data and survey marks (pegs, bench marks etc.) necessary for setting out. If this information is available, state how it can be obtained e.g. identify and supply the survey. If it is not, state how it is to be provided by the owner e.g. source, timing, or leave it to the architect to sort out.

#### Survey marks

See ABIC MW-2018 clause G1. Protection of the contractor’s survey marks is the contractor’s business.

Definition: A survey peg, bench mark, reference mark, signal, alignment, level mark or any other mark used or intended to be used for the purpose of setting out, checking or measuring the work.

Care of survey marks: Preserve and maintain the owner’s survey marks in their true positions.

Rectification: If survey marks are disturbed or obliterated, immediately rectify.

#### Safety

See ABIC MW-2018 clause G2 on contractor’s obligations for health and safety.

Blanket bans on toxic products may be worth considering, though this issue is best dealt with by specifying non-toxic alternatives at the appropriate place in the technical specification. Handling of existing asbestos is dealt with in 0201 Demolition. On lead hazards in construction, see AS 4874.

The contractor is subject to stringent public and Work Health and Safety law. Work Health and Safety (WHS) legislation in some states and territories also include statutory obligations on designers in relation to WHS issues arising out of their designs during and after construction. Neither the construction contract nor the designers consultancy agreement can limit these statutory obligations, but may add further requirements, such as the following paragraphs, that provide for the owner to be kept informed, through the architect, if certain events occur.

It is important to note that WHS obligations on contractors and designers differ in each state and territory.

Accidents: Promptly notify the architect of the occurrence of the following:

Accidents involving death or personal injury.

Accidents involving loss of time.

Incidents with accident potential such as equipment failure, slides and cave-ins.

Accident reports: Submit reports of accidents.

Purpose of submission: Information only.

#### Contractor's representative

See ABIC EW-1 clause G3 The requirement for full-time competent supervisors, with appropriate experience and training, may need to be documented in some cases. Requirements vary across the country for many trades. General plumbers and electricians (special class) must be licensed in every state and territory.

General: Must be accessible, and fluent in English and technical terminology.

#### Subcontracting

General: Submit a complete list of proposed subcontractors and suppliers.

See ABIC EW-1 clause G4 on subcontracting.

#### Program of work

ABIC EW-1 does not require a construction program. Delete this clause if a program is not required.

Construction program: Show the following:

Sequence of work.

Allowance for holidays.

Activity inter-relationships.

External dependencies including provision of access, document approvals and work by others.

Periods within which various stages or parts of the work are to be executed.

Revise default submission requirements, as necessary. For example, time frames and their relationship to the contract dates.

Time scale: Working days.

Updated program: Identify changes since the previous version, and show the estimated percentage of completion for each item of work.

Frequency:

e.g. Monthly; Before each site meeting.

Program chart: Display in the contractor’s site office an up-to-date bar chart and network diagram based on the construction program.

#### Order of work schedule

| Portion of work | Order of work | Time of work |
| --- | --- | --- |

If it is necessary to direct the contractor to perform the works in a particular order, or to complete stages or parts of the work in a particular sequence or at stated times, give the directions here. For example, the contractor will need to know the dates by which different parts of an existing building will be vacated, or the beginning and end of the building season (if any) in a national park or campus. Alternatively, the directions may be given in the form of a construction program issued to the contractor as part of the contract documents. Either way the requirements are contractual, unlike the program of work.

#### Site meetings

The owner may be invited to attend or send a representative to observe but not necessarily to participate in site meetings. Agendas may be required on large projects.

General: Hold and attend site meetings throughout the contract and arrange for the attendance of appropriate subcontractors, the architect, and appropriate consultants.

Frequency:

The frequency of meetings is best agreed by the architect and contractor, as being the most appropriate for the project, and may vary. It is helpful if meetings coincide with the timing of progress claims, though not essential.

Minutes: Make a record of site meetings. Within 5 working days after each meeting, distribute a copy of the minutes to each party.

Delete if the architect is to take and distribute the minutes.

Purpose of submission: Review.

Contacts: At the first site meeting, submit names and telephone numbers of responsible persons who may be contacted after hours during the course of the contract.

Purpose of submission: Information only.

### Completion of the works

See ABIC EW-1 Section M.

#### Reinstatement

General: Before completion, clean and repair damage caused by installation or use of temporary work and restore existing facilities used during construction to original condition.

#### Adjoining property

Evaluation: At practical completion, for each property described in the Adjoining properties to be recorded schedule, inspect the property with the architect and owner and occupant of the property, recording any damage that has occurred since the pre-commencement inspection.

#### Removal of plant

General: Within 10 working days of notice of completion, remove temporary works and construction plant no longer required. Remove the balance before the end of the security period.

### Payment for the works

See ABIC EW-1 Section N. It is assumed that any contingency sum is reserved outside the contract.

#### Import costs

See ABIC EW-1 clause N1 on import costs and contract price. Include only if risk of change is being taken by the owner. It is contrary to the policy of many public sector authorities. In such cases, delete the subclause.

Definition: Import costs include costs attributable to exchange rates, customs and import duty of imported content of items purchased for incorporation in the works.

Adjustment: If there are changes in rates applying to import costs of items listed in the Import cost adjustment schedule, add or deduct the amount of the difference to or from the contract sum, as applicable.

#### Import cost adjustment schedule

| Item | Country of origin | Import cost |
| --- | --- | --- |

#### Anticipated progress payments

See ABIC EW-1 clauses N3-N11. Ideally the schedule will address each trade or package, not just the total claim. This will be linked to the program of work.

General: At commencement of the works, submit a schedule of anticipated progress claims for the contract period. Submit a revised schedule with each progress claim.

Purpose of submission: Information only.

#### Progress claims

Break down: With each progress claim, submit a statement of amounts claimed in respect of each worksection or trade heading designated in the specification.

This subclause should be modified if there is a priced bill of quantities (not apparently anticipated in ABIC EW-1).

Purpose of submission: Review.

#### Method of measurement

General: In conformance with the principles of the Australian and New Zealand standard method of measurement of building works (ANZSMM).

### Miscellaneous

See ABIC EW-1 Section R.

#### Governing law

See ABIC EW-1 clause R8 Governing law. On Work Health and Safety requirements see ABIC EW-1 clause G2 Contractor’s obligations. The roles of private certifiers are not covered in these Notes or in this Commentary, and vary between jurisdictions.

Requirements of authorities: The owner, before entering into the contract, has given the notices, paid the fees, and obtained the permits, approvals and other authorisations stated in the Prior applications and approvals schedule.

On Work Health and Safety requirements, the roles of private certifiers vary between jurisdictions.

#### Prior applications and approvals schedule

| Prior notices given and applications made | Fees paid | Permits, approvals and authorisations received |
| --- | --- | --- |

See ABIC EW-1 clause A5 Obligations of owner. The owner is obliged to obtain and give the contractor any official documents required to begin the works.

List the applications made, e.g. Building application to Council, fees paid, and approvals received, e.g. Building approval dated.

This information may also be provided in 0121 Tendering, if so delete.

#### Authority conditions schedule

| Authority | Document | Condition |
| --- | --- | --- |

Authorities commonly impose conditions governing noise, access, dust, hours of operation, inspections and traffic control. The contractor is obliged by law to comply with environmental protection legislation and with local authority requirements. The contract cannot interfere with that obligation, but may stipulate more stringent requirements for contract purposes. Consider documenting any such requirements here in a separate schedule. Responsibility for conditions, if any, imposed by local authorities needs to be resolved. Consider scheduling here those conditions which affect the contractor. Coordinate with Site restrictions Site limitations. Ultimately, all the conditions are the responsibility of the applicant (owner) as far as the local authorities are concerned.

REFERENCED DOCUMENTS

The following documents are incorporated into this worksection by reference:

AS/NZS 1801	1997	Occupational protective helmets

ABIC EW-1	2003	Australian Building Industry Contract - Early Works Contract

ANZSMM	2018	Australian and New Zealand standard method of measurement of building works

The following documents are mentioned only in the Guidance text:

AS 2124	1992	General conditions of contract

AS 2436	2010	Guide to noise and vibration control on construction, demolition and maintenance sites

AS 4000	1997	General conditions of contract

AS 4874	2000	Guide to the investigation of potentially contaminated soil and deposited dust as source of lead available to humans

AS 4902	2000	General conditions of contract for design and construct

AS 4905	2002	Minor works contract conditions (Superintendent administered)

ABIC BW 2018 C	2018	Australian Building Industry Contract - Commercial basic works contract

ABIC MW-2018	2018	Australian Building Industry Contract – Major works

ABIC SW-2018	2018	Australian Building Industry Contract – Simple works

NCW4	2019	General conditions of contract for construction

NATSPEC GEN 016	2018	Preliminaries and contract schedules